## Iteration ... (hidden)
[17 empty] | Demo to TSB |  |  | FPT Final Release | [11 empty] | TSB Final Release
| Detail plan for Iteration 1 | [11 empty] | TSB's Holiday |  |  | JP's Holiday
No |  | Task | % | PIC | Status | Start | End | hours | Iteration 6 | [11 empty] | Iteration 7
2012-10-01
1899-12-31
1 | 2 | [7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
1 |  | Function A | bar: 1899-12-31 Sat to 1899-12-31 Sun; 1899-12-31 Wed
2 | T-2 |  | 100% | Hiep | Done | 2012-10-02 | 2012-10-02 | 2 | bar: 1899-12-31 Sat to 1899-12-31 Sun; 1899-12-31 Wed
3 | T-3 |  | 100% | OnSite | Done | 2012-10-08 | 2012-10-08 | 10 | bar: 1899-12-31 Sat to 1899-12-31 Sun; 1899-12-31 Wed
4 | T-4 |  | 100% | OnSite | Done | 2012-10-08 | 2012-10-08 | 10 | bar: 1899-12-31 Sat to 1899-12-31 Sun; 1899-12-31 Wed
5 | T-5 | [6 empty] | 50 | bar: 1899-12-31 Sat to 1899-12-31 Sun; 1899-12-31 Wed
|  | Total | [5 empty] | 72 | bar: 1899-12-31 Sat to 1899-12-31 Sun; 1899-12-31 Wed
Risk
R-1
R-2
R-3
Dependency
| D-1 | [7 empty] | 1899-12-31 Tue: Deliverables (○):
| D-2 | [7 empty] | 1899-12-31 Tue: 2012Oct09: #1 Demo to TSB
| D-3 | [7 empty] | 1899-12-31 Tue: 2012Oct11: #2 Demo to TSB
Issue
I-1
I-2
I-3
Change Request
CR-1 | bar: 1899-12-31 Thu
CR-2 | bar: 1899-12-31 Thu
- Delete log of current device on S3
- Delete all record of this device on Recommendation on DB
Wrong: ví dụ, http://s-f.c.hdex.jp/tc-guideframe-tv/calender/cal_mnth_gd.html
Correct: ví dụ, http://s-f.c.hdex.jp/tc-guideframe-tv/guide-template1.html?calender/cal_mnth_gd.html
Gọi thử 2 cái URL và so sánh là biết liền sai như thế nào.
TODAY

## TABLET_WBS (hidden)
TCS_TC_WBS (TSB Tablet & Apple Iphone)
Effort (person-days)
No | Task Particulars | Requirement | Design | Coding | Testing | Total | Volume
| SF-001-T - Display no officical sence list | [5 empty] | 1.211%
2 | Check official sence on the server | 0.2 | 0.25 | 1 | 0.4 | 1.85
| SF-002-T - Display no suitable content on device | [5 empty] | 1.211%
5 | Check the content is suitable or not with the device (this case is not suitable) | 0.2 | 0.25 | 1 | 0.4 | 1.85
| SF-040-T - Select Program Screen | [5 empty] | 5.074%
| List out all candidate program follow Name setting | 0.1 | 0.75 | 0.5 | 0.2 | 1.55
| List out all candidate program follow Chanel setting | 0.1 | 0.75 | 0.5 | 0.2 | 1.55
| List out all candidate program follow Start Date setting | 0.1 | 0.75 | 0.5 | 0.2 | 1.55
| List out all candidate program follow Start Time setting | 0.1 | 0.75 | 0.5 | 0.2 | 1.55
| List out all candidate program without sort criterias setting | 0.1 | 0.75 | 0.5 | 0.2 | 1.55
| SF-003-T - Refinement program | [5 empty] | 18.27%
| Setting Program Name to filter | 0.1 | 0.5 | 0.5 | 0.2 | 1.3
| Setting Chanel to filter (Five type of chanel) |  |  |  | 0
| - 地上デジタル | 0.1 | 0.5 | 0.5 | 0.2 | 1.3
| - BSデジタル ( can be expand) | 0.1 | 0.5 | 0.5 | 0.2 | 1.3
| - 110度CSデジタル | 0.1 | 0.5 | 0.5 | 0.2 | 1.3
| - スカパー | 0.1 | 0.5 | 0.5 | 0.2 | 1.3
| - CATV | 0.1 | 0.5 | 0.5 | 0.2 | 1.3
| Setting Start date to filter (Display Calendar screen) | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Setting Start Time | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Other Setting | 0 |  |  | 0
| - Grouped by program name at the same time | 0.6 | 0.5 | 3 | 1.2 | 5.3
| - Grouped by program name in the same CH | 0.6 | 0.5 | 3 | 1.2 | 5.3
| - Not together | 0.6 | 0.5 | 3 | 1.2 | 5.3
| SF-050-T - Select Tag List | [5 empty] | 4.124%
7 | Get program information from backend. | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Get list of tag list with the selected program from backend | 0 |  |  | 0
| - Official Scence | 0.2 | 0.5 | 1 | 0.4 | 2.1
| - None-Officical Scence | 0.2 | 0.5 | 1 | 0.4 | 2.1
| SF-070-T - Display Detail of Official Scence with TV | [5 empty] | 9.296%
| Get program information from backend. | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Get List of scence with name and other information | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display yahoo shop | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display scence information | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display Control button and control TV via CESI | 0.4 | 0.5 | 2 | 0.8 | 3.7
| Sync with TV real time (jum sence) | 0.2 | 0.5 | 1 | 0.4 | 2.1
| SF-060-T - Display Detail of None - Official Scence with TV | [5 empty] | 7.594%
| Get program information from backend. | 0.4 | 0.5 | 2 | 0.8 | 3.7
| Get List of scence with name and other information | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display Control button and control TV via CESI | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Sync with TV real time (jum sence) | 0.4 | 0.5 | 2 | 0.8 | 3.7
| SF-080-T - Diplay Detail Scence Infor | [5 empty] | 8.642%
| Display scence information | 0.4 | 0.5 | 2 | 0.8 | 3.7
| Display relate Link | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display more information | 0.4 | 0.5 | 2 | 0.8 | 3.7
| Display Control button and control TV via CESI | 0.4 | 0.5 | 2 | 0.8 | 3.7
| SF-090-T - Display on web brower | [5 empty] | 1.047%
| Display website | 0.2 |  | 1 | 0.4 | 1.6
| SP-010-T - Display hot keyword | [5 empty] | 2.095%
| TBD | 0.4 |  | 2 | 0.8 | 3.2
| TBD - Search / select devices Screen | [5 empty] | 3.404%
| TBD | 0.4 | 2 | 2 | 0.8 | 5.2
| SP-020-T - Yahoo hot key word | [5 empty] | 8.969%
| Display list of scence order by TV in the house | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display scence information | 0.4 | 0.5 | 2 | 0.8 | 3.7
| Display Yahoo shop | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display scence information | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display Control button and control TV via CESI | 0.4 | 0.5 | 2 | 0.8 | 3.7
| SP-030-T - Search Screen | [5 empty] | 11.39%
| Search keyword | 0.4 | 0.5 | 2 | 0.8 | 3.7
| Display list of scence order by TV in the house | 0.4 | 0.5 | 2 | 0.8 | 3.7
| Display scence information | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display Yahoo shop | 0.4 | 0.5 | 2 | 0.8 | 3.7
| Display scence information | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display Control button and control TV via CESI | 0.2 | 0.5 | 1 | 0.4 | 2.1
| SP-040-T - Display more scence Information | [5 empty] | 5.499%
| Display scence information | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display Yahoo shop | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display scence information | 0.2 | 0.5 | 1 | 0.4 | 2.1
| Display Control button and control TV via CESI | 0.2 | 0.5 | 1 | 0.4 | 2.1
| SP-050-T - Display on web brower | [5 empty] | 1.047%
| Display website | 0.2 |  | 1 | 0.4 | 1.6
| Display TC Header | [5 empty] | 11.13%
| Display icomming message | 0.6 | 1 | 3 | 1.2 | 5.8
| Display current control TV | 0.6 |  | 3 | 1.2 | 4.8
| Refresh button | 0.2 |  | 1 | 0.4 | 1.6
| Vitual Remote | 0.6 |  | 3 | 1.2 | 4.8
| Total | 15.5 | 28.75 | 77.5 | 31 | 152.75
Risk:
| R1 - Requirement will provide slow |  |  |  | 2% | 3.055
| R2 - TV from TSB to VN impact to the schedule. |  |  |  | 2% | 3.055
| R3 - Technical issue relating to remove TV via Tablet |  |  |  | 2% | 3.055
| R4 - Take time to intergrate to the other team (TEG, CM, CAL) |  |  |  | 2% | 3.055
Development work
| Deployment |  |  |  | 5% | 7.6375
| Support for Acceptance Test |  |  |  | 2% | 3.055
Overhead management
| Project management |  |  |  | 5% | 7.6375
| Communicator |  |  |  | 5% | 7.6375
| Toshiba Android Tablet |  |  |  |  | 190.9375 | pds | 8.679 | man/month
| Apple Iphone (in case of Iphone will develop Pararell Android) | 15.5 | 57.5 | 65.875 | 26.35 | 226.3582 | pds | 10.289 | man/month
| Total (Android & Iphone) |  |  |  |  | 417.2957 | pds | 20.8648 | man/month

## Iteration II (hidden)
| Detail plan for Iteration 1 | [11 empty] | TSB's Holiday
No |  | Task | % | PIC | Status | Start | End | hours | Iteration 1
2012-11-01
[9 empty] | 1900-01-18 | [11 empty] | 1899-12-31 | 1900-01-01
1 | 2 | [7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
1 |  | Task from Action Plan phase II
41 | T-41 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
42 | T-42 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
43 | T-43 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
44 | T-44 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
45 | T-45 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
46 | T-46 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
47 | T-47 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
48 | T-48 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
49 | T-49 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
3 | T-3 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
2 | T-2 |  | 0% |  | Not Done | 2012-10-02 | 2012-10-02
4 | T-4 |  | 0% |  | Not Done | 2012-10-08 | 2012-10-08
5 | T-5
|  | Total | [5 empty] | 0
Risk
| R-1 | Description 1
R-2
R-3
Dependency
| D-1 | Pre-staging enviroment from TSB | [6 empty] | 1900-01-18 Tue: Deliverables (○):
| D-2 | [7 empty] | 1900-01-18 Tue: 2012Oct09: #1 Demo to TSB
| D-3 | [7 empty] | 1900-01-18 Tue: 2012Oct11: #2 Demo to TSB
Issue
| I-1 | QATCTV-1228 - Can not reproduce
| I-2 | QATCTV-1096 - Can not reproduce
| I-3 | QATCTV-1325 - Can not reproduce
Change Request
CR-1 | bar: 1900-01-18 Thu
CR-2 | bar: 1900-01-18 Thu
- Delete log of current device on S3
- Delete all record of this device on Recommendation on DB
Wrong: ví dụ, http://s-f.c.hdex.jp/tc-guideframe-tv/calender/cal_mnth_gd.html
Correct: ví dụ, http://s-f.c.hdex.jp/tc-guideframe-tv/guide-template1.html?calender/cal_mnth_gd.html
Gọi thử 2 cái URL và so sánh là biết liền sai như thế nào.
TODO
Changing stream time
| Effort | 158
15.8
5 Test
10 dev
2 backend
TODAY

## General
Detail plan for Iteration 1 (3-Dec --> 14-Dec)
No |  | Task | Requirement | % | PIC | Status | Start | End | hours | Iteration 1
2012-12-03
[10 empty] | 1900-01-02 | [11 empty] | 1899-12-31 | 1900-01-01
1 | 2 | [8 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
1 | 1 | Scene continuous playback
2 | 2 | SP-020 |  | 0% | DucTA3 | In Progress | 2012-12-04 | 2012-12-05
3 |  | SP-050 |  | 0% | DucTA3 | In Progress | 2012-12-04 | 2012-12-05
4 |  | Operation Guide |  | 0% | TungAVG | Done | 2012-12-04 | 2012-12-05 | 2 | bar: 1900-01-02 Mon to 1900-01-02 Tue; 1900-01-02 Thu to 1900-01-01 Sun
5 |  | Coding for Playing screen |  | 0% | DucTA3 | In Progress | 2012-12-04 | 2012-12-05
6 |  | Play control: Switch/jump/skip/pause/stop scene |  | 0% | DucTA3
7 |  | Scene Play |  | 0% | ThanhDC4/TuanNA15C | In Progress | 2012-12-07
8 |  | Play from Inbox |  | 0% | TuanLHD | In Progress | 2012-12-07
9 |  | Module bán hàng
10 |  |  |  | 0% |  | Not Done
11 |  |  |  | 0% |  | Not Done
12 |  | Module Happy coins |  | 0% |  | Not Done
13 |  | Trúng ngay |  | 0% |  | Not Done
14 |  | Đổi quà
15 |  | Đấu giá ngược
Vé số may mắn
|  | Quà tặng |  | 0% |  | Not Done
Amazing!
|  | Module Easy coins |  | 0% |  | Not Done
|  | Oẳn tì tì |  | 0% |  | Not Done
|  | Bắn cung |  | 0% |  | Not Done
|  | Điểm danh |  | 0% |  | Not Done
|  | Chia sẻ facebook |  | 0% |  | Not Done
|  | Mời bạn bè |  | 0% |  | Not Done
|  | Module trang cá nhân |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  | Module admin |  | 0% |  | Not Done
|  | Quản lý người dùng |  | 0% |  | Not Done
|  | Quản lý sản phẩm |  | 0% |  | Not Done
|  | Quản lý chương trình sự kiện |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  |  |  | 0% |  | Not Done
|  | Total | [6 empty] | 0
Risk
| R-1 | Missing documentation have to provide on time
R-2
R-3
Dependency
| D-1 | Need specification for : The list of recommendation scene from friends. | [7 empty] | 1900-01-02 Tue: Deliverables (○):
| D-2 | [8 empty] | 1900-01-02 Tue: 2012Oct09: #1 Demo to TSB
| D-3 | [8 empty] | 1900-01-02 Tue: 2012Oct11: #2 Demo to TSB
Issue
| I-1 | We don't have TV with timeshift content
| I-2 | We don't have TV with more than 2 hard disks
I-3
Change Request
CR-1 | bar: 1900-01-02 Thu
CR-2 | bar: 1900-01-02 Thu
- Delete log of current device on S3
- Delete all record of this device on Recommendation on DB
Wrong: ví dụ, http://s-f.c.hdex.jp/tc-guideframe-tv/calender/cal_mnth_gd.html
Correct: ví dụ, http://s-f.c.hdex.jp/tc-guideframe-tv/guide-template1.html?calender/cal_mnth_gd.html
Gọi thử 2 cái URL và so sánh là biết liền sai như thế nào.
TODO
TODAY

## MAC-Address (hidden)
Open Bandwidth
http://front-int.tsbctv.com/tc-front-tv/cindex.html
http://s-f.c.hdex.jp/tc-front-tv/cindex.html
https://jenkins.tsbctv.com
http://s-ci.c.hdex.jp/
PC
No | Member | IP address | Mac Address | Computer name | Start date | End date
1 | AnhNV16 |  | E8-40-F2-3D-B5-6D | AnhNV16-F11 | 2012-10-09 | 2012-12-30
2 | DucTA3 |  | E0-CB-4E-8C-35-BB | DucTA3-F11 | 2012-10-09 | 2012-12-30
3 | HungNH2 |  | ‎4C-72-B9-20-A7-43 | HungNH2-F11 | 2012-10-09 | 2012-12-30
4 | PhuongHTL1 |  | E8-40-F2-3D-B4-4F | PhuongHTL1-F11 | 2012-10-09 | 2012-12-30
5 | NguyenLK2 | 10.88.66.62 | 38-60-77-F1-3F-76 | NguyenLK2-F11 | 2012-10-09 | 2012-12-30
6 | TuanBA5C |  | 4C-72-B9-20-A8-31 | TuanBA5C-F11 | 2012-10-09 | 2012-12-30
7 | TuanNA15C |  | 4c-72-b9-20-a7-e6 | TuanNA15C-F11 | 2012-10-09 | 2012-12-30
8 | TungAVG5C |  | 4C-72-B9-20-A7-BC | TungAVG5C-F11 | 2012-10-09 | 2012-12-30
9 | PhungNTK |  | 00 1C C0 FD 1D 70 | PhungNTK-F11 | 2012-10-09 | 2012-12-30
10 | Hainp |  | E8-40-F2-3D-B6-83 | Hainp-F11 | 2012-10-09 | 2012-12-30
11 | HiepHN |  | 4C-72-B9-20-A5-86 | HiepHN-F11 | 2012-10-09 | 2012-12-30
12 | ThanhDM |  | 4C-72-B9-20-A7-F1 | ThanhDM-F11 | 2012-10-09 | 2012-12-30
13 | VanNT4 |  | 00-1C-25-37-D5-80 | VanNT4-F11 | 2012-10-09 | 2012-12-30
14 | HoangNVM5C |  | E8-40-F2-3D-B5-99 | HoangNVM5C-F11 | 2012-10-09 | 2012-12-30
15 | PhuocLD |  | 00-27-0E-0A-22-85 | PhuocLD-F11 | 2012-10-09 | 2012-12-30
16 | TinND |  | 4C-72-B9-20-A8-64 | TinND-F11 | 2012-10-09 | 2012-12-30
17 | HungLv5C |  | 00-1C-C0-FD-0C-EA | HungLv5C-F11 | 2012-10-09 | 2012-12-30
18 | HaiNT18 |  | 00-27-0E-0A-24-C0 | HaiNT18-F11 | 2012-10-09 | 2012-12-30
19 | TuanLHD |  | 4C-72-B9-20-A8-52 | TuanLHD-F11 | 2012-10-09 | 2012-12-30
20 | AnhBNKD | 10.88.6.162 | 4C-72-B9-31-68-5B | AnhBNKD-F11 | 2012-11-29 | 2013-03-30
21 | ThanhDC4 | 10.88.6.149 | E0-69-95-01-50-E7 | ThanhDC4-F11 | 2012-11-29 | 2013-03-30
22 | ThongLV | 10.88.6.143 | E8-40-F2-3D-B5-50 | ThongLV-F11 | 2012-11-29 | 2013-03-30
TV
|  | Tên | Địa chỉ MAC | Địa chỉ IP
|  | Timecloud-5 (Z7) | E8-E0-B7-3F-5B-9E | 10.88.66.50
|  | Timecloud-4 | E8-E0-B7-70-5E-9E | 10.88.66.59
|  | Calendar-2 | E8-E0-B7-D4-5D-9E | 10.88.66.65
|  | Calendar-3 | E8-E0-B7-6E-5E-9E | 10.88.66.68
|  | Calendar-4 | E8-E0-B7-6F-5E-9E | 10.88.66.71
|  | Timecloud-1 | E8-E0-B7-D3-5D-9E | 10.88.66.24
|  | Menu-3 | E8-E0-B7-6C-5E-9E | 10.88.66.74
|  | Menu-1 | E8-E0-B7-D7-5D-9E | 10.88.66.73
|  | Calendar-1 | E8-E0-B7-D5-5D-9E | 10.88.66.72
|  | Menu-2 | E8-E0-B7-D6-5D-9E | 10.88.66.76
|  | Menu-4 | E8-E0-B7-6D-5E-9E | 10.88.66.77
|  | TimeCloud-3 | E8-E0-B7-71-5E-9E | 10.88.66.75

## Q&A (hidden)
Chức năng List recommend scene from friend
Nội dung
Display the list of recommendation scene from friend.
Sorted by program start time and scene start time like Ph2.
Q&A
Tài liệu back end chỉ định api sẽ được sử dụng cho màn hình này ?
Chức năng Kininaru! Check
Ghi nhận lại vị trí đang xem cho recommendation server
Những scene đã được check bằng kininaru key sẽ hiển thị lên màn hình sceneplay (Sp-051)
Q&A
Tài liệu back end chỉ định register position scene và get registered scene
Vẫn chưa hiểu Support DMP playback for taglist service
Nút view comment, tác dụng như thế nào.

## Ref 1- Documents... (hidden)
------------------------------------DOCUMENTATION TASK-----------------------------------------------------------------------
Scope:
- for all module of phase II
- For 3 team: TC, CAL, CM
Start date: 20/11/2012
End date: 30/11/2012
Deliverable:
- Software Architect.
- Design Document.
----------------------------------------------------------------------------------------------------
Document for:
- Our understanding your SW architecture.
- Check product specification and design specification:
o TSB try to read source code.
- Check CESI calling from TV side.
o Check CESI call run well or not. à make ore test case to test ?????
o Engineer side need to check.
- Re-create test Spec.
o Doer: TSB.
o Try to understand all over the structure.
1st Design Document:
- Like current.
- English version.
2nd Design Document should have (explain the way we use in our application):
- Sequence chart:
o Call API timing (GIS)
o Menu service.
o CESI service.
o Data Revise timing.
- Module Structure.
o Client Module Relation
o Basic structure.
- Framework:
o TEG framework and relation
- API
o Common module
o Menu Relate module
o CESI
o Backend.
§ Call back
§ Direct call.
§ ….

## Release Plan (hidden)
Dear All
We inform you next release plan. Could you see following plan.
And if you have any question or comment, Please tell me us.
Next Version :
Phase2.0.4
Release date:
2011-11-30 2:00(JST)
Schedule( All times are JST):
Today to 11/27 12:00
Commit fixing code into Phase2_Release
11/27 12:00
Code Frizzes on Phase2_Release
11/27 PM
SCM team deploy for Staging Server
11/27 PM – 11/28 17:00
QA Team test on Staging Server and inform Dev team about side effect.
Dev Team revise side effect.
11/29 AM
Complete revise side effect.
11/29 PM
Approve release by manager
11/30 2:00
SCM Team deploy for production server.
Manage target bugs:
We would like to manage target bugs on JIRA.
First, TSB Team shall set Priority and Fix Version/s field on JIRA Issues.
Next, TSB Team will request to fix bugs.
Then, WizTiVi/FPT Team will fix bugs along JIRA.
Please confirm JIRA Task board view.
1) Login QA TOSHIBA CLOUD TV Project.
2) Open [Agile]-[Task board].
3) Select “Phase2.0.4-GA” Version
Please attach screen capture image.
Test Environment:
We are preparing CI2(CI for Phase2). CI2 will deploy from Phase2_Release branch head automatically.
But, CI2 is not complete prepare.
Until then, We will deploy Staging Server from Phase2_Release at 17:00(JST) everyday.
But, I’m sorry. Today(11/21)’s deployment skip. We will deploy at 11/22 9:00(JST).
Best Regards,
Koji Maruya
*********************************************
ソフトウェア技術センター プロセス・品質技術開発担当
丸屋 宏二(Koji Maruya)
E-Mail: koji.maruya@toshiba.co.jp
*********************************************
【機密保持のお願い】
送信したメ－ルには、個人情報や機密情報が含まれている
場合があります。誤って送信されたメ－ルを受信された場合
には、誠に恐れ入りますが、このメ－ルのコピ－、使用、
公開等をなさらず、速やかに送信元にご連絡頂くとともに、
このメ－ルを削除頂きますようお願い申し上げます。
*English
The information contained in this email message
may be confidential information.
Please be careful if you forward, copy or print this message.
If you have received this email in error, please immediately
advise the sender by return email and delete the message.

## Phase III (hidden)
Hi anh Vinh
Em gui noi dung mail cua KH
@Anh Cuong: Nho anh xem dum em co gi sai sot ko nhe!!!
■Loai S
Hổ trợ gỡ ra hoặc gắn USB HDD vào | DucTA3
Trường hợp tháo USB HDD thì không thề tìm kiếm
Trường hợp gắn USB HDD vào thì có thề tìm kiếm từ HDD.
Play continute
■Loại A
Gửi URL của Shopping site đến tablet
Chuyển đổi các URL của Shopping site tương ứng từ TV đến tablet
Đối ứng cho trường hợp chỉ có tablet
Hiển thị thông tin chi tiết của CM
Phân chia các CM và hiển thị bằng 気になる！シーンリスト
Upload Log
Upload Log của các hoạt động
Thay đổi Top Menu của ScenePlay (thay đổi UI của SP)
Tìm kiếm CM
Có thể tìm kiếm CM ở ScenePlay
■Loại B
Chỉnh sửa lại lổi về sự chênh lêch vị trí Tab jump
Thêm setting offset của tag jump
Xem xét lại toàn bộ flow tag list
Đối ứng với tag list của search scene
Xóa search history |  | Hai tren
Multi chanel
Trường hợp chương trình đã được phát sóng từ Sub channel và Main Channel là giống nhau thì ở Sub Channel củng được hổ trợ chức năng [ 気になる！シーンリスト]
Send the full string of program title
Gửi string của program title dài 40 ký tự ( trước đây bị cắt nếu dài hơn 23 ký tự ) |  | TuanBA
Code screen flow khi play scene của Redcomment to friend
Code phần screen flow khi start play từ Inbox
Processing candidate program
Tập hợp các similar program sau khi filter và Hiển thị ra
Improved start-up speed of the quick -> tag list |  | TuanNa & Nguyen
Improved start-up speed of the quick -> kininaru key
Optimize phạm vi tìm kiếm khi thay đổi seeting của TimeShift
Không include những scene tại thời điểm thay đổi [TimeShift Machine Seeting] sang [No] vào đối tượng search
Thay đổi UI của SP
Xóa Preview, Thêm pain ở bên trái
Vấn đề 1 taglist
Sự chênh nhau giữa EPG và MData
Vấn đề 2 về tag list
Đối ứng các vấn đề phát sinh từ cục phát sóng